## Risk analysis
[Event] | [Date]
Explanation of colour coding
| Minor danger | Limited danger | Dangerous | Critical | Catastrophic
Very unlikely | Monitor | Monitor | Monitor | Monitor | Manage | 1
Unlikely | Monitor | Monitor | Monitor | Manage | Eliminate | 2
Possible | Monitor | Monitor | Manage | Eliminate | Eliminate | 3
Likely | Monitor | Manage | Eliminate | Eliminate | Eliminate | 4
Very likely | Manage | Eliminate | Eliminate | Eliminate | Eliminate | 5
| 1 | 2 | 3 | 4 | 5
Event | Cause | Likelihood |  | Effect |  | Action | Who is responsible | Action taken
Note on B4: Övergående, lindriga obehag
Note on C4: Enstaka skadade, varaktigt obehag.
Note on D4: Enstaka svårt skadade, svåra obehag, mindre evakuering.
Note on E4: Blomgren, Sofie: Enstaka döda, flera svårt skadade, större evakuering.
Note on F4: Flera dödade och skadade.

## Example risk analysis, clarify
Midsummer celebrations | 24/06/2016
Explanation of colour coding
| Minor danger | Limited danger | Dangerous | Critical | Catastrophic |  | Instructions: Fill in the matrix below. The boxes in the first column will automatically be coloured according to the different values given.
Very unlikely | Monitor | Monitor | Monitor | Monitor | Manage | 1
Unlikely | Monitor | Monitor | Monitor | Manage | Eliminate | 2
Possible | Monitor | Monitor | Manage | Eliminate | Eliminate | 3
Likely | Monitor | Manage | Eliminate | Eliminate | Eliminate | 4
Very likely | Manage | Eliminate | Eliminate | Eliminate | Eliminate | 5
| 1 | 2 | 3 | 4 | 5
Event | Cause | Likelihood |  | Effect |  | Action | Who is responsible | Action taken
Long queue | Entrance area too small, inefficient entry process, unexpectedly large number of people. | 4 | Likely | 2 | Limited danger | Queuing system with barriers to form a zig-zag, option to create more zig-zag sections, information given to people in the queue. | Safety Manager Anna Andersson | Planning carried out 20/05/2015. Details delegated to entry stewards. Checks on-site two hours before opening.
Fainting next to the stage | Dehydration, too much alcohol, too much pressure at front of stage. | 4 | Likely | 3 | Dangerous | Distribution of water, staff in place in stage pit in front, responsible sales in the bar. | Safety Manager Anna Andersson, Bar Manager Bengt Bengtsson, Concert Head Robin Robinsdotter. | No.
Personal injury in darts competition | Unclear delineation of competition area and public area. Intoxicated participants. | 3 | Possible | 2 | Limited danger | Mark out the competition area with rope. Have public stewards on site to ensure members of the public do not get in the way of the darts. Breathalyse the participants before the start. | Competition Manager Sten Stensson | Plan prepared 25/04/2016.
Noise complaints from neighbours | Noise level too high, no information before the event, wind blowing in their direction. | 3 | Possible | 1 | Minor danger | Send out information in good time prior to event. Be clear with sound techs about permitted levels. Invite neighbours to the festival for free. | Project Manager Jonas Jonasson | No.
Explanations:
Eliminate means that the risk should be eliminated entirely or prevented with such powerful means that it can be assumed to be eliminated.
Manage may mean, for example, using different means to reduce the likelihood of the risk occurring and/or to minimise in advance the damage effects the risk would cause.
Monitor means that the risk is monitored - no direct action taken to reduce the risk.
This risk analysis model is taken from the Events Safety Guide from the Swedish Civil Contingencies Agency.
Note on B4: Transient, minor discomfort
Note on C4: Individuals injured, lasting discomfort.
Note on D4: Individuals seriously injured, severe discomfort, minor evacuation.
Note on E4: Individuals killed, several seriously injured, major evacuation.
Note on F4: Multiple deaths and injuries.